## Sheet1
Task # | Task | Remarks | Estimate (HRs) | Start Date | End Date | Assigned To | Actual Completion Date
1 | Prep - everyone to have laptops/workstations with starUML, MS Office/OpenOffice, MS Project, Visio, Eclipse , JDK 1.6, Junit, UI Design tool(Jigloo???) |  | 4 | 14/3 | 14/3 | Team
2 | Identify Roles and Responsibilities - Proj Manager, Config Manager, Test Manager, Technical Lead. |  | 4 | 14/3 | 14/3 | Team
| Coding Standards |  | 2 | 14/3 | 14/3 | Puneet
3 | UML design
3.1 | Class Diagram |  | 8 | 14/3 | 15/3 | Team
4 | Framework design.
4.1 | Utility classes, reusable components, Exception Handling classes. |  | 8 | 18/3 | 18/3 | Team
5 | Preare System Test Plan |  | 8 | 19/3 | 19/3 | Jerry
6 | Detailed Design + DLD documentation | Explain classes methods, iplementation level detail. Multiple DLD documents | 16 | 19/3 | 20/3
7 | Group Review of DLD |  | 4 | 20/3 | 20/3
8 | Code Framework classes using TDD approach |  | 16 | 21/3 | 22/3
9 | Code core functionality using TDD approach | Start after starting the framework classes above | 320 | 22/3 | 28/3
10 | Static Code Analysis |  | 1 | 29/3 | 29/3
11 | Code integration |  | 8 | 30/3 | 30/3
12 | System/Integration Testing
12.1 | Cycle 1 |  | 12 | 31/3 | 2013-04-01
12.2 | Cycle 2 |  | 4 | 2013-04-01 | 2013-04-01
12.3 | Review Test Results of Cycle 1, Cycle 2 |  | 1 | 2013-04-01 | 2013-04-01
13 | Package the final product |  | 4 | 2013-04-02 | 2013-04-02
14 | Prepare run.bat, compile.bat |  | 4 | 2013-04-02 | 2013-04-02
14.1 | Final System/Integration Testing
14.2 | Cycle 3 |  | 4 | 2013-04-03 | 2013-04-03
15 | Review Test Results of Cycle 3 |  | 1 | 2013-04-03 | 2013-04-03
16 | Code Delivery |  |  | 2013-04-03 | 2013-04-03